Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date: 08-03-2026 |  |
| --- | --- |
| Team ID: SWTID-2026-3105 |  |
| Project Name: Product inventory management |  |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Backend Setup | USN-1 | Initialize Node.js project and configure Express server | 6 | High | Avaneesh |
| Sprint-1 | Database Setup | USN-2 | Connect MongoDB Atlas and create database structure | 6 | High | Avaneesh |
| Sprint-1 | User Model | USN-3 | Create User schema with password hashing | 8 | High | Avaneesh |
| Sprint-2 | JWT Authentication | USN-4 | Implement register and login APIs with JWT token | 8 | High | Avaneesh |
| Sprint-2 | Auth Middleware | USN-5 | Create JWT verification middleware for protected routes | 6 | High | Avaneesh |
| Sprint-2 | Product Model | USN-6 | Design Product schema linked with userId | 6 | High | Avaneesh |
| Sprint-3 | Product CRUD APIs | USN-7 | Implement Add, Get, Update, Delete product APIs | 10 | High | Avaneesh |
| Sprint-3 | Search API | USN-8 | Implement product search/filter endpoint | 6 | Medium | Avaneesh |
| Sprint-3 | Authorization Logic | USN-9 | Ensure users can access only their own products | 6 | High | Avaneesh |
| Sprint-4 | Error Handling | USN-10 | Implement centralized error handling middleware | 6 | Medium | Avaneesh |
| Sprint-4 | API Testing | USN-11 | Test APIs using Postman and validate responses | 5 | Medium | Avaneesh |
| Sprint-4 | Backend Optimization | USN-12 | Improve API performance and validation checks | 5 | Medium | Avaneesh |

Project Tracker, Velocity & Burndown Chart: (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 5 Days | 17 Feb 2026 | 21 Feb 2026 | 20 | 21 Feb 2026 |
| Sprint-2 | 20 | 5 Days | 22 Feb 2026 | 26 Feb 2026 | 20 | 26 Feb 2026 |
| Sprint-3 | 22 | 5 Days | 27 Feb 2026 | 3 Mar 2026 | 22 | 3 Mar 2026 |
| Sprint-4 | 16 | 4 Days | 4 Mar 2026 | 8 Mar 2026 | 16 | 8 Mar 2026 |